## Al Amin Bin Shafiq
To-do list
To be completed by: |  |  |  | Name: Al Amin Bin Shafiq
Deadline: |  |  |  | Date: 12/13/2022
Final Project
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | First Meeting | 2022-12-02 | 2022-12-02 |  | 1
100% | Add/Remove Entities | 2022-12-02 | 2022-12-02 |  | 1
100% | Add/Remove Attributes | 2022-12-02 | 2022-12-02 |  | 1
100% | Entity Relationships | 2022-12-03 | 2022-12-03 |  | 1
100% | Unique Indexes | 2022-12-06 | 2022-12-07 |  | 2
100% | Second Meeting | 2022-12-07 | 2022-12-07 |  | 1
100% | Add UserAuthorization Table | 2022-12-08 | 2022-12-08 |  | 1
100% | Attribute Nullability | 2022-12-09 | 2022-12-09 |  | 1
100% | Create History Tables | 2022-12-10 | 2022-12-10 |  | 1
100% | Third Meeting | 2022-12-11 | 2022-12-11 |  | 1
100% | Load data to SQL server | 2022-12-12 | 2022-12-13 |  | 2
100% | Presentation | 2022-12-14 | 2022-12-15 |  | 2
100% | Final Meeting | 2022-12-15 | 2022-12-15 |  | 1

## Gregory Guevara
To-do list
To be completed by: |  |  |  | Name: Gregory Guevara
Deadline: |  |  |  | Date: 12/13/2022
Final Project
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | First Meeting | 2022-12-02 | 2022-12-02 |  | 1
100% | Add/Remove Entities | 2022-12-02 | 2022-12-02 |  | 1
100% | Add/Remove Attributes | 2022-12-02 | 2022-12-02 |  | 1
100% | Create Domain Structure | 2022-12-03 | 2022-12-03 |  | 1
100% | Executive Overview | 2022-12-04 | 2022-12-06 | 2022-12-11 | 3 | Revisions regarding the scope of the executive overview
100% | Create Default Values | 2022-12-04 | 2022-12-06 |  | 3
100% | Domain Definitions | 2022-12-05 | 2022-12-06 |  | 2
100% | Unique Indexes | 2022-12-06 | 2022-12-07 |  | 2
100% | Second Meeting | 2022-12-07 | 2022-12-07 |  | 1
100% | Create Views | 2022-12-11 | 2022-12-11 |  | 1
100% | Third Meeting | 2022-12-11 | 2022-12-11 |  | 1
100% | Forward Engineering | 2022-12-12 | 2022-12-12 |  | 1
100% | Presentation | 2022-12-14 | 2022-12-15 |  | 2
100% | Final Meeting | 2022-12-15 | 2022-12-15 |  | 1

## Mohammed Kabir
To-do list
To be completed by: |  |  |  | Name: Mohammed Kabir
Deadline: |  |  |  | Date: 12/13/2022
Final Project
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | First Meeting | 2022-12-02 | 2022-12-02 |  | 1
100% | Entity Definitions | 2022-12-04 | 2022-12-04 |  | 1
100% | Second Meeting | 2022-12-07 | 2022-12-07 |  | 1
100% | Add UserAuthorization Table | 2022-12-08 | 2022-12-08 |  | 1
100% | Create Themes for Archetypes | 2022-12-09 | 2022-12-09 |  | 1
100% | Pascal Case Conversion | 2022-12-09 | 2022-12-09 |  | 1
100% | Subject Areas | 2022-12-10 | 2022-12-10 |  | 1
100% | Third Meeting | 2022-12-11 | 2022-12-11 |  | 1
100% | Migrate model to PostgreSQL | 2022-12-13 | 2022-12-13 |  | 1
100% | Presentation | 2022-12-14 | 2022-12-15 |  | 1
100% | Final Meeting | 2022-12-15 | 2022-12-15 |  | 1

## Fidiana Mujaj
To-do list
To be completed by: |  |  |  | Name: Fidiana Mujaj
Deadline: |  |  |  | Date: 12/13/2022
Final Project
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | First Meeting | 2022-12-02 | 2022-12-02 |  | 1
100% | Add/Remove Entities | 2022-12-02 | 2022-12-02 | 2022-12-04 | 1 | Required some revisions to add attributes and expand entities
100% | Add/Remove Attributes | 2022-12-02 | 2022-12-02 |  | 1
100% | Created Project Tasks | 2022-12-03 | 2022-12-04 |  | 2
100% | Table Normalization | 2022-12-04 | 2022-12-05 |  | 2
100% | Second Meeting | 2022-12-07 | 2022-12-07 |  | 1
100% | Attribute Nullability | 2022-12-09 | 2022-12-09 |  | 1
100% | Theme Revisions | 2022-12-10 | 2022-12-10 |  | 1
100% | Create History Tables | 2022-12-10 | 2022-12-10 |  | 1
100% | Create Audit Table Triggers | 2022-12-11 | 2022-12-11 |  | 1
100% | Create Views | 2022-12-11 | 2022-12-11 |  | 1
100% | Third Meeting | 2022-12-11 | 2022-12-11 |  | 1
100% | Forward Engineering | 2022-12-12 | 2022-12-12 |  | 1
100% | Load data to SQL server | 2022-12-12 | 2022-12-13 |  | 2
100% | Migrate model to PostgreSQL | 2022-12-13 | 2022-12-13 |  | 1
100% | Migrate model to MySQL | 2022-12-13 | 2022-12-13 |  | 1
100% | Presentation | 2022-12-14 | 2022-12-15 |  | 2
100% | Final Meeting | 2022-12-15 | 2022-12-15 |  | 1

## Ismahan Siddiqui
To-do list
To be completed by: |  |  |  | Name: Ismahan Siddiqui
Deadline: |  |  |  | Date: 12/13/2022
Final Project
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | First Meeting | 2022-12-02 | 2022-12-02 |  | 1
100% | To Do Planner | 2022-12-04 | 2022-12-04 |  | 1
100% | Second Meeting | 2022-12-07 | 2022-12-07 |  | 1
100% | Pascal Case Conversion | 2022-12-09 | 2022-12-09 |  | 1
100% | Create Audit Table Triggers | 2022-12-11 | 2022-12-11 |  | 1
100% | Create Themes for Archetypes | 2022-12-09 | 2022-12-09 |  | 1
100% | Subject Areas | 2022-12-10 | 2022-12-10 |  | 1
100% | Third Meeting | 2022-12-11 | 2022-12-11 |  | 1
100% | Migrate model to MySQL | 2022-12-13 | 2022-12-13 |  | 1
100% | Presentation | 2022-12-14 | 2022-12-15 |  | 2
100% | Final Meeting | 2022-12-15 | 2022-12-15 |  | 1

## Nathaniel Wiradiradja
To-do list
To be completed by: |  |  |  | Name: Nathaniel Wiradiradja
Deadline: |  |  |  | Date: 12/13/2022
Final Project
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | First Meeting | 2022-12-02 | 2022-12-02 |  | 1
100% | Add/Remove Entities | 2022-12-02 | 2022-12-02 |  | 1
100% | Add/Remove Attributes | 2022-12-02 | 2022-12-02 |  | 1
100% | Create Domain Structure | 2022-12-03 | 2022-12-03 |  | 1
100% | Create Validations | 2022-12-05 | 2022-12-06 |  | 2
100% | Validation Definitions | 2022-12-04 | 2022-12-06 |  | 3
100% | Second Meeting | 2022-12-07 | 2022-12-07 |  | 1
100% | Create Schemas for Domains | 2022-12-08 | 2022-12-08 |  | 1
100% | Theme Revisions | 2022-12-09 | 2022-12-09 |  | 1
100% | Create Views | 2022-12-11 | 2022-12-11 |  | 1
100% | Third Meeting | 2022-12-11 | 2022-12-11 |  | 1
100% | Presentation Template | 2022-12-12 | 2022-12-13 |  | 2
100% | Load data to SQL server | 2022-12-12 | 2022-12-13 |  | 2
100% | Presentation | 2022-12-14 | 2022-12-15 |  | 2
100% | Final Meeting | 2022-12-15 | 2022-12-15 |  | 1